## Executive Summary
Raceup Hub — Migration to master CDN
Audit 29 HTML pages · Plan to move from direct sheet/hardcoded → master.raceup.co.th
EXECUTIVE SUMMARY
Audit 29 หน้าใน raceup-hub พบว่า:
• 4 หน้า ✅ Migrated แล้ว (Phase D Wave 3): post-event, sponsor-update, project-assign, project-assign-dashboard
• 6 หน้า — LOW complexity (แค่ replace hardcoded array): index, projects, racepack-stock, leave-dashboard, leave-summary, ot-admin
• 3 หน้า — MEDIUM complexity (refactor admin email + event list): leave-form, ot-form, ot-report
• 4 หน้า — SKIP (own data, ไม่เกี่ยว master): rank, returning, stat (historical 47 events) + social-dashboard
• 12 หน้า — NO REFACTOR NEEDED (utility/UI pages ไม่ใช้ data): bib-maker, budget, calendar, cowork, etc.
ระยะเวลาประมาณ:
• Quick wins (LOW): 6 หน้า × 5 นาที = 30 นาที
• Medium: 3 หน้า × 15 นาที = 45 นาที
• Total: ~1.5 ชั่วโมง สำหรับการ migrate ทั้งหมด
ประโยชน์:
• Admin email lists อัพเดทอัตโนมัติเมื่อเพิ่ม/ลบพนักงาน
• Event lists อัพเดททันทีเมื่อทีมแก้ Working Sheet
• ลบ duplicate hardcoded data ในหลายไฟล์
• Single source of truth — Hub Link Sheet เป็นหลัก

## Page Inventory
Raceup Hub — 29 Pages Inventory
Page | Purpose | Data Source | Status | Migration Priority | Effort
post-event.html | Post-event data dashboard | master CDN (events) + Hub Apps Script (post-event data) | DONE | Wave 3c | —
sponsor-update.html | Sponsor tracking per event | master CDN (events) + Hub Apps Script | DONE | Wave 3a | —
project-assign.html | Project assignment matrix | master CDN (events + project-assign) | DONE | Wave 3b | —
project-assign-dashboard.html | Project workload dashboard | master CDN (events + project-assign + staff) | DONE | Wave 3b | —
index.html | Hub homepage | Hardcoded email + Master Numbers Sheet URL | LOW | P1 | 5 min
racepack-stock.html | Race pack inventory | Hardcoded 8 events + 8 admin emails | LOW | P1 | 10 min
projects.html | Project portfolio overview | Hardcoded Scenic series codes | LOW | P1 | 5 min
leave-dashboard.html | HR leave dashboard (admin) | Hardcoded ADMIN_EMAILS (2 emails) | LOW | P1 | 5 min
leave-summary.html | HR leave summary (admin) | Hardcoded ADMIN_EMAILS (2 emails) | LOW | P1 | 5 min
ot-admin.html | HR OT admin | Hardcoded admin email check (1 email) | LOW | P1 | 5 min
leave-form.html | HR leave form (staff) | Own Hub Apps Script (leave records) | MED | P2 | 15 min
ot-form.html | HR OT form (staff) | Own Hub Apps Script (OT records) | MED | P2 | 15 min
ot-report.html | HR OT report | Own Hub Apps Script (OT records) | MED | P2 | 15 min
rank.html | Runner ranking (47+ events) | race-data.js (historical archive 2016-2026) | SKIP | — | —
returning.html | Returning runners analysis | race-data.js (historical archive) | SKIP | — | —
stat.html | Runner statistics dashboard | race-data.js (historical archive) | SKIP | — | —
social-dashboard.html | Social media dashboard | Own Apps Script with own data | SKIP | — | —
warehouse.html | Warehouse mgmt | Own Apps Script with own data | SKIP | — | —
event-history.html | Event archive viewer | Own data — events.html aggregates | SKIP | — | —
bib-maker.html | BIB number generator (uses local files) | No external data | OK | — | —
budget.html | Budget tool | Hub Apps Script + Numbers Sheet (separate domain) | OK | — | —
calendar.html | Calendar view | Hub Apps Script | OK | — | —
cowork.html | Cowork dashboard | Hub Apps Script | OK | — | —
info.html | Static info page | No data | OK | — | —
insight.html | Insight dashboard | Hub Apps Script | OK | — | —
invoice.html | Invoice tool | Hub Apps Script | OK | — | —
library.html | Library/docs page | No data | OK | — | —
petty-cash.html | Petty cash tool | Hub Apps Script | OK | — | —
qr.html | QR code generator | No data | OK | — | —
tools.html | Tools page | No data | OK | — | —

## Migration Plan
Migration Plan — Step by Step
Wave | Page | What to Change | Pattern | Time
Wave 5a | racepack-stock.html | Replace 8 hardcoded events array → window.RACEUP_EVENTS | + master CDN events.js | 10 min
Wave 5a | racepack-stock.html | Replace STOCK_ADMIN_EMAILS (8 emails) → window.RACEUP_STAFF filter by role | + master CDN staff.js | 5 min
Wave 5b | leave-dashboard.html | Replace ADMIN_EMAILS [2] → filter staff by Level=C level | + master CDN staff.js | 5 min
Wave 5b | leave-summary.html | Same as leave-dashboard | + master CDN staff.js | 5 min
Wave 5b | ot-admin.html | Replace admin check → filter staff by Level=C level | + master CDN staff.js | 5 min
Wave 5c | projects.html | Replace hardcoded Scenic codes → filter events by series=Scenic | + master CDN events.js | 5 min
Wave 5d | index.html | Replace hardcoded email + Numbers Sheet URL | + master CDN staff.js | 5 min
Wave 6a | leave-form.html | Add event dropdown from master events | + master CDN events.js | 15 min
Wave 6b | ot-form.html | Add event dropdown from master events | + master CDN events.js | 15 min
Wave 6c | ot-report.html | Add event filter from master events | + master CDN events.js | 15 min
Test | All migrated pages | Smoke test — open in Chrome, check console for "from master CDN" | F12 verify | 15 min
Commit | raceup-hub repo | git add + commit + push | CMD | 2 min
Deploy | Cloudflare Pages auto-deploy | Wait for build | auto | 3 min

## Refactor Patterns
Code Patterns for Migration
PATTERN 1: Hardcoded events array
const events = ['KYM26','PSMH26','CSMH26',...] ↓ Replace with: <script src="https://master.raceup.co.th/data/events.js"></script> <script> const events = (window.RACEUP_EVENTS ¦¦ [ {code:'KYM26',name:'Khao Yai Marathon 2026',date:'2026-01-11'}, // ...fallback embedded ]).map(e => e.code); </script>
PATTERN 2: Hardcoded admin email list
const ADMIN_EMAILS = ['wisuta@raceup.co.th','alongkorn@raceup.co.th']; ↓ Replace with: <script src="https://master.raceup.co.th/data/staff.js"></script> <script> const ADMIN_EMAILS = (window.RACEUP_STAFF ¦¦ []) .filter(s => s.level === 'C level' ¦¦ s.role === 'Admin') .map(s => s.email) .filter(Boolean); // Fallback if CDN fails if (ADMIN_EMAILS.length === 0) { ADMIN_EMAILS.push('wisuta@raceup.co.th', 'alongkorn@raceup.co.th'); } </script>
PATTERN 3: Filter events by series
const SCENIC_CODES = ['PSMH26','CSMH26','RSMH26','KSMH26','CMSH26','NSM26']; ↓ Replace with: <script src="https://master.raceup.co.th/data/events.js"></script> <script> const SCENIC_CODES = (window.RACEUP_EVENTS ¦¦ []) .filter(e => e.series && e.series.indexOf('Scenic') !== -1) .map(e => e.code); </script>
PATTERN 4: Event dropdown for forms
<select id="event-select"> <option value="">เลือกงาน</option> </select> <script src="https://master.raceup.co.th/data/events.js"></script> <script> const sel = document.getElementById('event-select'); (window.RACEUP_EVENTS ¦¦ []).forEach(ev => { const opt = document.createElement('option'); opt.value = ev.code; opt.textContent = ev.code + ' — ' + ev.name + ' (' + ev.date + ')'; sel.appendChild(opt); }); </script>